## Jira.csv
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Description | Environment | Watchers | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Security Level | Custom field (Development) | Custom field (Issue color) | Custom field (Rank) | Sprint | Custom field (Start date) | Custom field (Story point estimate) | Team Id | Team Name | Custom field (Vulnerability) | Parent | Parent key | Parent summary | Status category | Status category changed
Auth & RBAC | ALC-1 | 10000 | Epic | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Medium |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 6:37 PM | 04/Oct/26 8:59 PM | 04/Oct/26 9:23 PM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} | yellow | 0¦hzzzzu: | [9 empty] | To Do | 04/Oct/26 6:37 PM
Resource Management | ALC-2 | 10001 | Epic | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Medium |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 6:37 PM | 04/Oct/26 8:59 PM | 04/Oct/26 8:59 PM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} | dark_green | 0¦i00002: | [9 empty] | To Do | 04/Oct/26 6:37 PM
Booking Engine & Concurrency | ALC-3 | 10002 | Epic | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Medium |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 6:39 PM | 04/Oct/26 8:59 PM | 04/Oct/26 8:59 PM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} | dark_blue | 0¦i0000c: | [9 empty] | To Do | 04/Oct/26 6:39 PM
Notification Engine | ALC-4 | 10003 | Epic | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Medium |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 6:39 PM | 04/Oct/26 9:01 PM | 04/Oct/26 9:01 PM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} | dark_orange | 0¦i0000e: | [9 empty] | To Do | 04/Oct/26 6:39 PM
Analytics and Alerting | ALC-5 | 10004 | Epic | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Medium |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 6:40 PM | 04/Oct/26 9:00 PM | 04/Oct/26 9:00 PM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} | dark_yellow | 0¦i0000n: | [9 empty] | To Do | 04/Oct/26 6:40 PM
Interactive Floor Map | ALC-6 | 10005 | Epic | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Medium |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 6:40 PM | 04/Oct/26 9:00 PM | 04/Oct/26 9:00 PM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} | dark_teal | 0¦i0000o: | [9 empty] | To Do | 04/Oct/26 6:40 PM
Devops & Docs | ALC-7 | 10006 | Epic | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Medium |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 6:40 PM | 04/Oct/26 9:33 PM | 04/Oct/26 9:33 PM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} | dark_grey | 0¦i0000w: | [9 empty] | To Do | 04/Oct/26 6:40 PM
As an employee, I can log in with username/password and receive a JWT | ALC-8 | 10007 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 6:47 PM | 04/Oct/26 9:34 PM | 04/Oct/26 9:31 PM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0000z: | SCRUM Sprint 1 |  | 3.0 |  |  |  | 10000 | ALC-1 | Auth & RBAC | To Do | 04/Oct/26 6:47 PM
Implement JWT refresh token endpoint | ALC-9 | 10008 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 6:48 PM | 04/Oct/26 10:28 PM | 04/Oct/26 10:29 PM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i00013: | SCRUM Sprint 1 |  | 2.0 |  |  |  | 10000 | ALC-1 | Auth & RBAC | To Do | 04/Oct/26 6:48 PM
Implement RBAC for 3 roles: Employee / Manager / Admin | ALC-25 | 10024 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:38 PM | 04/Oct/26 10:38 PM | 04/Oct/26 10:43 PM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0001o: | SCRUM Sprint 1 |  | 5.0 |  |  |  | 10000 | ALC-1 | Auth & RBAC | To Do | 04/Oct/26 10:38 PM
As an admin, I can create, edit, and delete user accounts | ALC-26 | 10025 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:43 PM | 04/Oct/26 10:45 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0001u: | SCRUM Sprint 1 |  | 3.0 |  |  |  | 10000 | ALC-1 | Auth & RBAC | To Do | 04/Oct/26 10:43 PM
As an admin, I can assign role and department to a user | ALC-27 | 10026 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:44 PM | 04/Oct/26 10:45 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i00027: | SCRUM Sprint 1 |  | 2.0 |  |  |  | 10000 | ALC-1 | Auth & RBAC | To Do | 04/Oct/26 10:44 PM
As an admin, I can create, edit, and delete resources (rooms, equipment) | ALC-29 | 10028 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:46 PM | 04/Oct/26 10:49 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i00029: | SCRUM Sprint 1 |  | 5.0 |  |  |  | 10001 | ALC-2 | Resource Management | To Do | 04/Oct/26 10:46 PM
As an admin, I can configure operating hours for each resource | ALC-30 | 10029 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:46 PM | 04/Oct/26 10:49 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0002a: | SCRUM Sprint 1 |  | 3.0 |  |  |  | 10001 | ALC-2 | Resource Management | To Do | 04/Oct/26 10:46 PM
As an admin, I can assign a resource to a zone / floor | ALC-31 | 10030 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:46 PM | 04/Oct/26 10:49 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0002b: | SCRUM Sprint 1 |  | 2.0 |  |  |  | 10001 | ALC-2 | Resource Management | To Do | 04/Oct/26 10:46 PM
As a user, I can view the resource list and resource detail | ALC-32 | 10031 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:47 PM | 04/Oct/26 10:49 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0002b:i | SCRUM Sprint 1 |  | 3.0 |  |  |  | 10001 | ALC-2 | Resource Management | To Do | 04/Oct/26 10:47 PM
As a user, I can view and edit my own profile | ALC-28 | 10027 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Medium |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:44 PM | 04/Oct/26 10:45 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0002c: | SCRUM Sprint 2 |  | 2.0 |  |  |  | 10000 | ALC-1 | Auth & RBAC | To Do | 04/Oct/26 10:44 PM
As a user, I can filter resources by type, zone, and status | ALC-33 | 10032 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:48 PM | 04/Oct/26 10:49 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0003g: | SCRUM Sprint 2 |  | 3.0 |  |  |  | 10001 | ALC-2 | Resource Management | To Do | 04/Oct/26 10:48 PM
As a user, I can view available time slots for a resource by day | ALC-34 | 10033 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:50 PM | 04/Oct/26 10:50 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0003i: | SCRUM Sprint 2 |  | 3.0 |  |  |  | 10002 | ALC-3 | Booking Engine & Concurrency | To Do | 04/Oct/26 10:50 PM
As a user, I can create a booking and the system checks for conflicts | ALC-35 | 10034 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:50 PM | 04/Oct/26 10:50 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0003r: | SCRUM Sprint 2 |  | 5.0 |  |  |  | 10002 | ALC-3 | Booking Engine & Concurrency | To Do | 04/Oct/26 10:50 PM
System handles concurrent bookings and ensures only one succeeds | ALC-36 | 10035 | Technical Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:52 PM | 04/Oct/26 10:53 PM | 04/Oct/26 10:52 PM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0003s: | SCRUM Sprint 2 |  | 13.0 |  |  |  | 10002 | ALC-3 | Booking Engine & Concurrency | To Do | 04/Oct/26 10:52 PM
As a user, I can cancel my own booking | ALC-38 | 10037 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:53 PM | 04/Oct/26 10:53 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0004f: | SCRUM Sprint 2 |  | 2.0 |  |  |  | 10002 | ALC-3 | Booking Engine & Concurrency | To Do | 04/Oct/26 10:53 PM
As a manager, I can cancel any booking within my department | ALC-39 | 10038 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:53 PM | 04/Oct/26 10:54 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0004m: | SCRUM Sprint 2 |  | 2.0 |  |  |  | 10002 | ALC-3 | Booking Engine & Concurrency | To Do | 04/Oct/26 10:53 PM
As an admin, I can cancel any booking in the system | ALC-40 | 10039 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:54 PM | 04/Oct/26 10:54 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i00050: | SCRUM Sprint 2 |  | 1.0 |  |  |  | 10002 | ALC-3 | Booking Engine & Concurrency | To Do | 04/Oct/26 10:54 PM
As a user, I can view booking history scoped to my role | ALC-41 | 10040 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:55 PM | 04/Oct/26 10:55 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i00056: | SCRUM Sprint 2 |  | 3.0 |  |  |  | 10002 | ALC-3 | Booking Engine & Concurrency | To Do | 04/Oct/26 10:55 PM
As a user, I receive an in-app notification when my booking is confirmed | ALC-42 | 10041 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:55 PM | 04/Oct/26 10:55 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0005j: | SCRUM Sprint 3 |  | 3.0 |  |  |  | 10003 | ALC-4 | Notification Engine | To Do | 04/Oct/26 10:55 PM
Implement cron job to send usage reminders before booking start time | ALC-44 | 10043 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:56 PM | 04/Oct/26 10:56 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i00060: | SCRUM Sprint 3 |  | 5.0 |  |  |  | 10003 | ALC-4 | Notification Engine | To Do | 04/Oct/26 10:56 PM
As a user, I receive a notification when my booking is cancelled by someone else | ALC-45 | 10044 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:56 PM | 04/Oct/26 10:56 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i00064: | SCRUM Sprint 3 |  | 2.0 |  |  |  | 10003 | ALC-4 | Notification Engine | To Do | 04/Oct/26 10:56 PM
As a manager, I receive an alert when resource utilization exceeds 85% | ALC-46 | 10045 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:57 PM | 04/Oct/26 10:57 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0006f: | SCRUM Sprint 3 |  | 3.0 |  |  |  | 10003 | ALC-4 | Notification Engine | To Do | 04/Oct/26 10:57 PM
Implement email notification as a supplementary channel | ALC-47 | 10046 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Medium |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:57 PM | 04/Oct/26 10:57 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0006i: | SCRUM Sprint 4 |  | 5.0 |  |  |  | 10003 | ALC-4 | Notification Engine | To Do | 04/Oct/26 10:57 PM
As an admin, I can export a report as CSV or PDF | ALC-53 | 10052 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Medium |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 11:00 PM | 04/Oct/26 11:00 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0006n: | SCRUM Sprint 4 |  | 5.0 |  |  |  | 10004 | ALC-5 | Analytics and Alerting | To Do | 04/Oct/26 11:00 PM
Implement API: utilization rate per resource (weekly / monthly) | ALC-48 | 10047 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:58 PM | 04/Oct/26 10:58 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0006s: | SCRUM Sprint 3 |  | 5.0 |  |  |  | 10004 | ALC-5 | Analytics and Alerting | To Do | 04/Oct/26 10:58 PM
Implement API: booking trend over time | ALC-49 | 10048 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:58 PM | 04/Oct/26 10:58 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0006u: | SCRUM Sprint 3 |  | 3.0 |  |  |  | 10004 | ALC-5 | Analytics and Alerting | To Do | 04/Oct/26 10:58 PM
Implement cron job to check 85% threshold and trigger alert | ALC-50 | 10049 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:59 PM | 04/Oct/26 10:59 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i00073: | SCRUM Sprint 3 |  | 5.0 |  |  |  | 10004 | ALC-5 | Analytics and Alerting | To Do | 04/Oct/26 10:59 PM
As an admin, I can view a system-wide summary dashboard | ALC-51 | 10050 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:59 PM | 04/Oct/26 10:59 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i00074: | SCRUM Sprint 3 |  | 5.0 |  |  |  | 10004 | ALC-5 | Analytics and Alerting | To Do | 04/Oct/26 10:59 PM
As a manager, I can view a utilization report scoped to my department | ALC-52 | 10051 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 10:59 PM | 04/Oct/26 10:59 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0007c: | SCRUM Sprint 3 |  | 3.0 |  |  |  | 10004 | ALC-5 | Analytics and Alerting | To Do | 04/Oct/26 10:59 PM
As an admin, I can upload a floor plan image | ALC-54 | 10053 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 11:00 PM | 04/Oct/26 11:00 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0007j: | SCRUM Sprint 4 |  | 3.0 |  |  |  | 10005 | ALC-6 | Interactive Floor Map | To Do | 04/Oct/26 11:00 PM
As an admin, I can map (x, y) coordinates to each room or desk on the floor plan | ALC-55 | 10054 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 11:01 PM | 04/Oct/26 11:01 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0007x: | SCRUM Sprint 4 |  | 5.0 |  |  |  | 10005 | ALC-6 | Interactive Floor Map | To Do | 04/Oct/26 11:01 PM
System renders SVG map with color coding: green (available) / red (booked) | ALC-56 | 10055 | Technical Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 11:01 PM | 04/Oct/26 11:01 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i00083: | SCRUM Sprint 4 |  | 8.0 |  |  |  | 10005 | ALC-6 | Interactive Floor Map | To Do | 04/Oct/26 11:01 PM
As a user, I can click an available room on the map to open the booking form | ALC-57 | 10056 | Story | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 11:02 PM | 04/Oct/26 11:02 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0008g: | SCRUM Sprint 4 |  | 3.0 |  |  |  | 10005 | ALC-6 | Interactive Floor Map | To Do | 04/Oct/26 11:02 PM
Set up Docker Compose for backend and PostgreSQL | ALC-58 | 10057 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  | HUY NGUYỄN HỒNG | 712020:3d2f2b91-c1cb-476f-9b95-174f9d37d452 | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 11:03 PM | 05/Oct/26 9:40 AM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0008l: | SCRUM Sprint 0 |  | 3.0 |  |  |  | 10006 | ALC-7 | Devops & Docs | To Do | 04/Oct/26 11:03 PM
Set up GitHub repository, branch strategy, and .gitignore | ALC-59 | 10058 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Highest |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 11:03 PM | 05/Oct/26 9:45 AM | 05/Oct/26 9:44 AM |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0008x: | SCRUM Sprint 0 |  | 1.0 | 73b0dd99-891e-47d2-ac1d-cf0b00a41a8c | My Team |  | 10006 | ALC-7 | Devops & Docs | To Do | 04/Oct/26 11:03 PM
Configure GitHub Actions CI to build and run tests on push | ALC-60 | 10059 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | Medium |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 11:03 PM | 04/Oct/26 11:04 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i00091: | SCRUM Sprint 2 |  | 5.0 |  |  |  | 10006 | ALC-7 | Devops & Docs | To Do | 04/Oct/26 11:03 PM
Write Swagger / OpenAPI documentation for all APIs | ALC-61 | 10060 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 11:03 PM | 04/Oct/26 11:05 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0009c: | SCRUM Sprint 4 |  | 5.0 |  |  |  | 10006 | ALC-7 | Devops & Docs | To Do | 04/Oct/26 11:03 PM
Write Postman collection and configure test environments | ALC-62 | 10061 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 11:03 PM | 04/Oct/26 11:05 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0009f: | SCRUM Sprint 3 |  | 3.0 |  |  |  | 10006 | ALC-7 | Devops & Docs | To Do | 04/Oct/26 11:03 PM
Write JUnit unit tests for Booking Service (coverage ≥ 70%) | ALC-63 | 10062 | Task | To Do | ALC | Alloca | software | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da |  | High |  |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | 04/Oct/26 11:04 PM | 04/Oct/26 11:05 PM |  |  |  | 0 |  |  | TÂN NGUYỄN THANH | 712020:3346084f-fe4e-4379-98f0-8f79a23dd7da | [8 empty] | {} |  | 0¦i0009p: | SCRUM Sprint 3 |  | 8.0 |  |  |  | 10006 | ALC-7 | Devops & Docs | To Do | 04/Oct/26 11:04 PM